## Slide 1: Uinta Basin Ozone SIP Progress
One year extension request submitted to EPA March 30, 2021
Monitoring data still indicates will not attain by August 3, 2022
Completed 2021 ozone season without an exceedance of the 2015 ozone standard so most likely will be eligible for second year extension to August 3, 2023
Would use 2020, 2021, and 2022 data to determine attainment for 2023
Therefore even with extension request most likely being granted, UDAQ still needs to continue to plan for SIP

## Slide 2: Uinta Basin Ozone SIP Progress
Inventory
    Almost complete for episodic (February 2013), baseline (2017) and on track to complete projected inventories for 2023 in June timeframe
    Completed VOC composition study updates to 2017 oil and gas emission inventory and very close on produced water pond inventory updates, will share when updated
    Next step is to run inventories through SMOKE model to support analysis for 15% RFP/ROP and photochemical modeling work
Photochemical Model
    Modeling group is currently focused on Wasatch Front and potential international transport demonstration

## Slide 3: Uinta Basin Ozone SIP Progress
RACT/RACM
    Received RACT analysis from major sources on State jurisdiction and UDAQ permitting staff will be working with sources
    Working through RACM evaluation of EPA oil and gas rules, CTGs, other state’s rules
    Beginning to evaluate baseline inventory and analyze where potential VOC reductions can be achieved
NNSR Program
    Final step for marginal ozone CAA requirements it to have NNSR permit program and off-sets established
    UDAQ is certifying that we have this program and offsets identified via R307-403
    Beginning to scope ERC banking rule and work with EPA and Tribe